## Test Plan - Velocity
Features | Write test case (FE) | Execution (FE) | SUM (FE) | Remarks
User Registration | 1 | 5 | 6
User login /logout | 1 | 5 | 6
Dashboard (Staff) - Search - Filter - Patient list - Patient info | 10 | 30 | 40
Download records | 1 | 5 | 6
Generate AI record | 10 | 20 | 30
AI Screening (User) | 5 | 10 | 15
[7 empty] | Lead 0.7*1 = 0.7 |  | Lead 0.7*1 = 0.7
[7 empty] | OS 0.9*1 = 0.9 |  | OS 0.9*2 = 1.8
[7 empty] | Total = 1.6 |  | Total = 2.5
|  | SIT (FE) | 113 |  |  |  | OS-1, Per-1 |  | OS-2, Per-1
|  | UAT (FE) | 40 |  | Task | MD (TCPrep+SIT+UAT) | QA-2 | Sprint | QA-3 | Sprint
|  | Total (FE) | 153 |  | Total | 153 | 95.625 | 11.9531 | 61.2 | 7.65
[5 empty] | SIT | 113 | 70.625 | 8.8281 | 45.2 | 5.65
[5 empty] | UAT | 40 | 26.6667 | 3.3333 | 16.6667 | 2.0833
**1 Sprint = 2 Weeks

## Test Plan - Timeline
Epic | Release | Task |  | SP119 |  | SP120 |  | SP121 |  | SP122 |  | SP123 |  | SP124 |  | SP125 |  | SP126 |  | SP127 |  | SP128 |  | SP1 |  | SP1 |  | SP2 |  | SP3 |  | SP4 |  | SP5 |  | SP6 |  | SP7 |  | SP8 |  | SP9 |  | SP10 |  | SP11 |  | SP141 |  | SP142 |  | SP143 |  | SP144 |  | SP145 |  | SP146 |  | SP147 |  | SP148 |  | SP149 |  | SP150 |  | SP151 |  | SP152 |  | SP153 |  | SP154 |  | SP155 |  | SP156 |  | SP157
|  |  | 2024-08-01 |  |  |  | 2024-09-01 |  |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-01 |  |  |  |  | 2025-07-01 |  |  |  | 2025-08-01 |  |  |  | 2025-09-01 |  |  |  |  | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  |  | 2026-01-01 |  |  |  | 2026-02-01
|  |  | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30 | 2025-01-06 | 2025-01-13 | 2025-01-20 | 2025-01-27 | 2025-02-03 | 2025-02-10 | 2025-02-17 | 2025-02-24 | 2025-03-03 | 2025-03-10 | 2025-03-17 | 2025-03-24 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 2025-04-21 | 2025-04-28 | 2025-05-05 | 2025-05-12 | 2025-05-19 | 2025-05-26 | 2025-06-02 | 2025-06-09 | 2025-06-16 | 2025-06-23 | 2025-06-30 | 2025-07-07 | 2025-07-14 | 2025-07-21 | 2025-07-28 | 2025-08-04 | 2025-08-11 | 2025-08-18 | 2025-08-25 | 2025-09-01 | 2025-09-08 | 2025-09-15 | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02
Agnos Health - Better AI | R1
|  | SIT - User Registration | 2024-12-01 2024-12-23: TC; 2025-01-01 2025-01-13: QA1; 2025-03-01 2025-03-24: Buffer to Retest Defect
|  | SIT - User login /logout | 2025-02-01 2025-02-03: QA1
|  | SIT - Dashboard (Staff) | 2025-01-01 2025-01-13: QA2 +; 2025-03-01 2025-03-10: QA1
|  | SIT - Download records | 2025-02-01 2025-02-24: QA1
|  | SIT - AI Screening (User) | 2025-01-01 2025-01-13: QA3
|  | SIT - Generate AI record | 2025-02-01 2025-02-03: QA3
|  | UAT - E2E | 2025-04-01 2025-04-07: 3 QA
|  | UAT - Regression | 2025-04-01 2025-04-21: 2QA

## Test Report
Test Progress
Feature | Number of testcase | Passed | Failed | Blocked | Inprogress | N/A | No Run | %Passed | Delayed !!
Registration | 20 | 12 | 1 | 2 | 1 | 1 | 3 | 60%
Login/Logout | 15 | 8 | 2 | 0 | 1 | 1 | 1 | 53.33%
Dashboard | 38 | 10 | 1 | 16 | 3 | 1 | 1 | 26.32%
Total | 73 | 30 | 4 | 18 | 5 | 3 | 5 | 41.1%
Defect
Number of Defect | Outstanding | Highest | High | Medium | Low | Lowest
4 | 4 | 1 | 2 | 1 | 0 | 0
For details of the test cases, please refer to : https://testcase.com
For details of the defects, please refer to : https://defects.com

## Registration
TS# | Test Scenarios | TC# | Test Cases | Test Steps | Expected results | Priority | Test Result | Defect No. | Test Data | Test By | Test Date | Automated ? | Remarks
TS01 | UI | TC01_01 | Verify design register page | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ | 1. Displays the UI according to the Figma design. | Low | Passed |  |  | Aimm | 8 Jul 2025 | N
TS02 | Register form | TC02_01 | Verify when do not input any data | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Do not input data | 1. The 'Confirm' button is disable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_02 | Verify when input incorrect email format | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input incorrect email format 3. Input the left data 4. Click 'Confirm' button | 1. The system displays error message "The email should be in the format 'test@example.com'" | Low | Passed |  | aimm@gmail | Aimm | 8 Jul 2025 | Y
|  | TC02_03 | Verify when input correct email format | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input correct email format | 1. The system allows to register | Low | Blocked | DF01 | aimm@gmail.com | Aimm | 8 Jul 2025 | Y
|  | TC02_04 | Verify when input incorrect password format | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ | 1. The system displays error message "The password must be at least 8 characters long and include at least one uppercase letter, one digit, and one special character." | Low | Passed |  | Aim1234 | Aimm | 8 Jul 2025 | Y
|  | TC02_05 | Verify when input correct password format | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ | 1. The system allows to register | Low | Failed | DF01 | ABCD12345! | Aimm | 8 Jul 2025 | Y
|  | TC02_06 | Verify when input only email | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input email | 1. The 'Confirm' button is disable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_07 | Verify when input only password | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input password | 1. The 'Confirm' button is disable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_08 | Verify when input only confirm password | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input confirm password | 1. The 'Confirm' button is disable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_09 | Verify when input only email and password | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input email and password | 1. The 'Confirm' button is disable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_10 | Verify when input email, password and confirm password | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input email, password and confirm password | 1. The 'Confirm' button is enable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_11 | Verify when input only password and confirm password | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input email, password and confirm password | 1. The 'Confirm' button is disable | Low | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_12 | Verify when input the same value in both the password and confirm password | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input correct email, 3. Input the same value password and confirm password 4. Click 'Confirm' button | 1. The system allows to register | High | Blocked | DF01 |  | Aimm | 8 Jul 2025 | Y
|  | TC02_13 | Verify when password and confirm password do not match | 1. Open register page https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Input correct email, 3. Input the difference value password and confirm password 4. Click 'Confirm' button | 1.The system displays error message Confirm password does not match the password. | Medium | Passed |  |  | Aimm | 8 Jul 2025 | Y
|  | TC02_14 | Verify password visibility toggle | 1. Open register page 2. Enter password 3. Click on eye icon to toggle password visibility | Password should be visible/hidden when toggling | Medium | Passed
TS03 | Compatibility | TC03_01 | Desktop - Chrome | 1. Open register page on desktop - Chrome https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Test and interact with the registration page functionalities. | 1. The registration feature work well 2. The UI not broken | High | Inprogress |  |  | Aimm | 8 Jul 2025 | Y
|  | TC03_02 | Desktop - Safari | 1. Open register page on desktop - Safari https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Test and interact with the registration page functionalities. | 1. The registration feature work well 2. The UI not broken | Low | No Run |  |  |  |  | Y
|  | TC03_03 | iPhone - Safari | 1. Open register page on iPhone - Chrome https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Test and interact with the registration page functionalities. | 1. The registration feature work well 2. The UI not broken | High | No Run |  |  |  |  | Y
|  | TC03_04 | iPhone - Facebook browser | 1. Open register page on iPhone - Facebook browser https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Test and interact with the registration page functionalities. | 1. The registration feature work well 2. The UI not broken | Low | N/A |  |  | Aimm | 8 Jul 2025 | N
|  | TC03_05 | Andriod - Chrome | 1. Open register page on Andriod - Chrome https://dev.app.agnoshealth.com/ai_dashboard/agnos/sign_up/ 2. Test and interact with the registration page functionalities. | 1. The registration feature work well 2. The UI not broken | High | No Run |  |  | Aimm | 8 Jul 2025 | Y

## LoginLogout
TS# | Test Scenarios | TC# | Test Cases | Test Steps | Expected results | Priority | Test Result | Defect No. | Test Data | Test By | Test Date | Automated ? | Remarks
TS01 | UI | TC01_01 | Verify design login and logout page | 1. Open login page | 1. The system displays the login design according to the Figma design | Low | Passed |  |  | Aimm | 9 Jul 2025 | N
TS02 | Login | TC02_01 | Verify login with valid credentials | 1. Open login page 2. Enter valid username and password 3. Click sign in button | 1. User successfully logged in and redirected to dashboard page | High | Passed |  | Username : test@gmail.com Password : 12345 | Aimm | 9 Jul 2025 | Y
|  | TC02_02 | Verify login with invalid password | 1. Open login page 2. Enter valid username and invalid password 3. Click sign in button | 1. Display error message: "Invalid username or password" | High | Passed |  | Username : test@gmail.com Password : wrongpassword | Aimm | 9 Jul 2025 | Y
|  | TC02_03 | Verify login with empty fields | 1. Open login page 2. Leave username and password fields empty 3. Click sign in button | 1. Sign in button is disable | Low | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC02_04 | Verify login with invalid username | 1. Open login page 2. Enter invalid username and valid password 3. Click sign in button | 1. Display error message: "Invalid username or password" | Low | Passed |  | Username : wrong@gmail.com Password : 12345 | Aimm | 9 Jul 2025 | Y
|  | TC02_05 | Verify password visibility toggle | 1. Open login page 2. Enter password 3. Click on eye icon to toggle password visibility | Password should be visible/hidden when toggling | Medium | Passed |  |  | Aimm | 9 Jul 2025 | Y
TS03 | Logout | TC03_01 | Verify when logout on dashboard page | 1. Login 2. On dashboard page click 'Logout' icon | 1. The system redirects to login page and log out the user. | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_02 | Verify when logout on patient info page | 1. Login 2. On dashboard page click 'Logout' icon | 1. The system redirects to login page and log out the user. | Low | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_03 | Verify when back on browser after logging out | 1. Login 2. On dashboard page click 'Logout' icon 3. Click back on browser | 1. After logging out, if the user clicks the browser's back button or accesses the direct URL, the system should redirect them to the login page. | Medium | Failed | DF03 |  | Aimm | 9 Jul 2025 | Y
|  | TC03_04 | Verify when access the derect link after logging out | 1. Login 2. On dashboard page click 'Logout' icon 3. Access the direct link , https://dev.app.agnoshealth.com/ai_dashboard/ | 1. After logging out, if the user clicks the browser's back button or accesses the direct URL, the system should redirect them to the login page. | Low | Failed | DF03 |  | Aimm | 9 Jul 2025 | Y
TS04 | Compatibility | TC04_01 | Desktop - Chrome | 1. Open login page on desktop - Chrome 2. Test and interact with the registration page functionalities. | 1. The login/logout feature work well 2. The UI not broken | Low | Inprogress |  |  | Aimm | 9 Jul 2025 | Y
|  | TC04_02 | Desktop - Safari | 1. Open register page on desktop - Safari 2. Test and interact with the registration page functionalities. | 1. The login/logout feature work well 2. The UI not broken | Low | No Run |  |  |  |  | Y
|  | TC04_03 | iPhone - Safari | 1. Open register page on iPhone - Chrome 2. Test and interact with the registration page functionalities. | 1. The login/logout feature work well 2. The UI not broken | Low | No Run |  |  |  |  | Y
|  | TC04_04 | iPhone - Facebook browser | 1. Open register page on iPhone - Facebook browser 2. Test and interact with the registration page functionalities. | 1. The login/logout feature work well 2. The UI not broken | Low | N/A |  |  | Aimm | 9 Jul 2025 | N
|  | TC04_05 | Andriod - Chrome | 1. Open register page on Andriod - Chrome 2. Test and interact with the registration page functionalities. | 1. The login/logout feature work well 2. The UI not broken | Low | No Run |  |  |  |  | Y

## Dashboard
TS# | Test Scenarios | TC# | Test Cases | Test Steps | Expected results | Priority | Test Result | Defect No. | Test Data | Test By | Test Date | Automated ? | Remarks
TS01 | UI | TC01_01 | Verify design dashboard page | 1.Login | 1. The system displays the dashboard design according to the Figma design | Low | Passed |  |  | Aimm | 9 Jul 2025 | N
TS02 | Download records | TC02_01 | Verify when click 'Download' button | 1. Login 2. On Dashboard page, click 'Download' button | 1. The confirm popup will be displayed 2. The design of the popup display follows the Figma design. | Low | Passed |  |  | Aimm | 9 Jul 2025 | N
|  | TC02_02 | Verify when click 'Confrim' button on confirm popup | 1. Login 2. On Dashboard page, Click 'Download' button 3. Click 'Confirm' button | 1. The CSV file is successfully downloaded to the user's machine after the download action is confirmed 2. The confirm pop up will disappear | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC02_03 | Verify when click 'Cancel' button on confirm popup | 1. Login 2. On Dashboard page, click 'Download' button 3. Click 'Confirm' button | 1. The CSV file will not start download 2. The confirm pop up will disappear | Medium | Passed |  |  | Aimm | 9 Jul 2025 | Y
TS03 | Search | TC03_01 | Verify when search with patient name | 1. Go to the dashboard page 2. Enter a valid patient name in the search field 3. Click Search | 1. System displays records that match the patient name | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_02 | Verify when search with patient contact | 1. Go to the dashboard page 2. Enter a valid patient contact number in the search field 3. Click Search | 1. System displays records that match the patient contact | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_03 | Verify when search with record id | 1. Go to the dashboard page 2. Enter a valid record ID in the search field 3. Click Search | 1. System displays the record that matches the record ID | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_04 | Verify when search with record code | 1. Go to the dashboard page 2. Enter a valid record code in the search field 3. Click Search | 1. System displays records that match the record code | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_05 | Verify search with partial matching keyword | 1. Go to the dashboard page 2. Enter a partial patient name 3. Click Search | 1. System displays all records containing the keyword John | Low | No Run |  |  |  |  | Y | The search icon will not able to click, Pls confirm with PO/BA
|  | TC03_06 | Verify search with empty input | 1. Go to the dashboard page 2. Leave the search field blank 3. Click Search | 1. System displays a message "Please enter search keyword" or no result | Low | Inprogress |  |  | Aimm | 9 Jul 2025 | Y
|  | TC03_07 | Verify search with invalid keyword | 1. Go to the dashboard page 2. Enter a random or invalid keyword in the search field and click Search 3. Click Search | 1. System displays "No records found" | Low | Passed |  |  | Aimm | 9 Jul 2025 | Y
TS04 | Navigation | TC04_01 | Verify default active tab on page load | 1. Go to the dashboard page | 1. By default, the Open tab is active and its records are displayed | High | Failed | DF04 |  | Aimm | 9 Jul 2025 | Y
|  | TC04_02 | Verify navigation to Open tab | 1. Go to the dashboard page 2. Click 'In progress tab' 3. Back to 'Open' tab | 1. The Open tab is active and system displays records with status Open | High | Blocked | DF04 |  |  |  | Y
|  | TC04_03 | Verify navigation to In Progress tab | 1. Go to the dashboard page 2. Click Click on the In Progress tab | 1. The In Progress tab is active and system displays records with status In Progress | High | Blocked | DF04 |  |  |  | Y
|  | TC04_04 | Verify navigation to Complete tab | 1. Go to the dashboard page 2. Click Click on the Complete tab | 1. The Complete tab is active and system displays records with status Complete | High | Blocked | DF04 |  |  |  | Y
|  | TC04_05 | Verify data count in each tab | 1. Go to the dashboard page 2. Click Click on the In Progress tab 3. Check the number of records displayed after selecting each tab | 1. The number of records displayed matches the actual data count in the system | Medium | Blocked | DF04 |  |  |  | Y
|  | TC04_06 | Verify persistence of selected tab after refresh | 1. Go to the dashboard page 2. Click Click on the In Progress tab 3. Refresh the page | 1. System displays message like "No records found" | Low | No Run |  |  |  |  | Y
|  | TC04_07 | Verify navigate of pagination | 1. Go to the dashboard page 2. Click Click on the In Progress tab 3. Click to page 2 | 1. System displays paginated results accordingly | High | No Run |  |  |  |  | Y
|  | TC04_08 | Verify navigate to patient info and back to dashboard page | 1. Go to the dashboard page 2. Click Click on the In Progress tab 3. Click any record 4. Click hamberger menu | 1. System back to dashboard page with default active tab | Low | No Run |  |  |  |  | Y
TS05 | Filter by triages | TC05_01 | Verify filter by All | 1. Go to the dashboard page 2. Select All option in triage filter | 1. System displays all records regardless of triage category | High | Inprogress |  |  | Aimm | 9 Jul 2025 | Y
|  | TC05_02 | Verify filter by Self Care | 1. Go to the dashboard page 2. Select Self Care option in triage filter | 1. System displays only records with triage = Self Care | High | Passed |  |  | Aimm | 9 Jul 2025 | Y
|  | TC05_03 | Verify filter by Seek Medical | 1. Go to the dashboard page 2. Select Seek Medical option in triage filter | 1. System displays only records with triage = Seek Medical | High | Blocked | DF04 |  |  |  | Y
|  | TC05_04 | Verify filter by Urgent | 1. Go to the dashboard page 2. Select Urgent option in triage filter | 1. System displays only records with triage = Urgent | High | Blocked | DF04 |  |  |  | Y
|  | TC05_05 | Verify filter by Emergency | 1. Go to the dashboard page 2. Select Emergency option in triage filter | 1. System displays only records with triage = Emergency | High | Blocked | DF04 |  |  |  | Y
|  | TC05_06 | Verify filter multiple triages | 1. Go to the dashboard page 2. Select Emergency option and Selt care in triage filter | 1. System displays only records with triage = Emergency and Self care | High | Blocked | DF04 |  |  |  | Y
TS06 | Filter by date | TC06_01 | Verify when do not select date | 1. Go to the dashboard page 2. Do not select date |  | Low | Blocked | DF04 |  |  |  | Y
|  | TC06_02 | Verify when select date as 'Today' | 1. Go to the dashboard page 2. Select date as 'Today' | 1. Ths system displays records with create today | High | Blocked | DF04 |  |  |  | Y
|  | TC06_03 | Verify when select date as 'This Week' | 1. Go to the dashboard page 2. Select date as 'This Week' | 1. Ths system displays records with create this week | High | Blocked | DF04 |  |  |  | Y
|  | TC06_04 | Verify when select date as 'Last Month' | 1. Go to the dashboard page 2. Select date as 'Last Month' | 1. Ths system displays records with create last week | High | Blocked | DF04 |  |  |  | Y
TS07 | Filter by channel | TS07_01 | Verify when select 'All' | 1. Go to the dashboard page 2. Select 'Agnos Application' channel | 1. System displays records with all channels | High | Blocked | DF04 |  |  |  | Y
|  | TS07_02 | Verify when select 'Agnos Application' | 1. Go to the dashboard page 2. Select 'Agnos Application' channel | 1. The system displays records with 'Agnos Application' channel | High | Blocked | DF04 |  |  |  | Y
|  | TS07_03 | Verify when select 'Vimut Hospital' | 1. Go to the dashboard page 2. Select 'Vimut Hospital'' channel | 1. The system displays records with 'Vimut Hospital'' channel | High | Blocked | DF04 |  |  |  | Y
|  | TS07_04 | Verify when select 'Vimut telemed' | 1. Go to the dashboard page 2. Select 'Vimut telemed' channel | 1. The system displays records with 'Vimut telemed' channel | High | Blocked | DF04 |  |  |  | Y
TS08 | Compatibility | TC08_01 | Desktop - Chrome | 1. Open dashboard page on desktop - Chrome 2. Test and interact with the registration page functionalities. | 1. The dashboardfeature work well 2. The UI not broken | Low | Inprogress |  |  | Aimm | 9 Jul 2025 | Y
|  | TC08_02 | Desktop - Safari | 1. Open dashboard page on desktop - Safari 2. Test and interact with the registration page functionalities. | 1. The dashboard feature work well 2. The UI not broken | Low | No Run |  |  |  |  | Y
|  | TC08_03 | iPhone - Safari | 1. Open dashboard page on iPhone - Chrome 2. Test and interact with the registration page functionalities. | 1. The dashboard feature work well 2. The UI not broken | Low | No Run |  |  |  |  | Y
|  | TC08_04 | iPhone - Facebook browser | 1. Open dashboard page on iPhone - Facebook browser 2. Test and interact with the registration page functionalities. | 1. The dashboard feature work well 2. The UI not broken | Low | N/A |  |  | Aimm | 9 Jul 2025 | N
|  | TC08_05 | Andriod - Chrome | 1. Open dashboard page on Andriod - Chrome 2. Test and interact with the registration page functionalities. | 1. The dashboardfeature work well 2. The UI not broken | Low | No Run |  |  | Aimm | 9 Jul 2025 | Y

## Defects
DF# | Description | Status | Priorty | Environment
DF01 | Subject : [Registration] The system does not allow registration when a correct password format is entered Step 1. Go to registration page 2. Input correct email (aimm@gmail.com) 3. Input correct password and confirm password (Abcd1234!) 4. Click 'Confirm' button Actual result : The system displays an error message and does not allow the user to register. Expected result : If the user inputs the correct password format, the system must allow the user to register without any errors. | Open | High | SIT
DF02 | Subject : [Download] Download records feature is not working well when data not found Step 1. Login (test@gmail.com/12345) 2. Do not search or filter 3. Click 'Download' button 4. Click 'Confirm' button Actual result : The 'Confirm' button is not working. Expected result : Able to download CSV file with empty data. | Open | Medium | SIT
DF03 | Subject : [Logout] The system does not properly log out the user, allowing access to the system even after logout. Step 1. Login (test@gmail.com/12345) 2. Click 'Logout' button 4. Click back on browser Actaul result : Able to access the system. Expected result : After logging out, if the user clicks the browser's back button or accesses the direct URL, the system should redirect them to the login page. | Open | High | SIT
DF04 | Subject : [Dashboard] The "Open" tab is the default active tab, but no records are displayed and the system shows a "Data not found" message. Step 1. Login (test@gmail.com/12345) Actual result : The system display no record found After try to select tab 'Complete' >>> 'Inprogress' >>> 'Open' , the records display normally Expected result : The Open tab is active and system displays records with status Open. Remark** It seems that the filter by triage is not working correctly. When switch the tab and apply multiple filters together returns incorrect results This defect blocked test case that relate to filter and we decided to test after this defect is fixed. | Open | Highest | SIT